## About
Excel → Odoo Data Migration Checklist (Bangladesh)
What this is
The 40-item migration checklist field-tested across manufacturing go-lives, plus the 10 Bangladesh master-data checks (BIN, TIN/TDS, opening stock from a physical count) and a reconciliation sheet.
How to use it
• Work through '40-item checklist' phase by phase; set status and dates.
• Use 'BD master data' to make sure the Bangladesh-specific fields are captured before import.
• After each trial load, fill 'Reconciliation': counts and sums must match source to the taka.
• Do not start cut-over until every Critical item is Done.
The full method behind this template
https://mhasan.me/lab/0008-excel-odoo-migration-checklist
Yellow cells are for your input. Formulas are in plain cells, so avoid overwriting them.
Free template by Mehedi Hasan, Odoo Certified Functional Consultant · mhasan.me · Free to use and adapt; please keep this credit line.
Version: 25 September 2026

## 40-item checklist
Phase | # | Task | Why it matters | Owner | Priority | Status | Named person | Due | Notes
1 · Inventory of truth | 01 | List every system, sheet and folder where business data currently lives. | Include the "shadow" spreadsheets people maintain on their own laptops. | BA + Ops Lead | Critical | Not started
1 · Inventory of truth | 02 | For each source, name the human owner — not the department. | A department doesn't answer email at 9 PM during cutover. | BA | Must-do | Not started
1 · Inventory of truth | 03 | Snapshot row counts and last-modified dates per sheet. | You're going to need this for reconciliation later. | Data Lead | Must-do | Not started
1 · Inventory of truth | 04 | Flag duplicate masters (e.g. two customer lists, three product catalogs). | Decide which is canonical before anyone touches a transformation script. | BA + Finance | Critical | Not started
1 · Inventory of truth | 05 | Identify all external feeds (banks, customs, marketplace, EDI). |  | IT | Must-do | Not started
1 · Inventory of truth | 06 | Document the data dictionary in business language, not column names. |  | BA | Must-do | Not started
1 · Inventory of truth | 07 | Confirm legal data retention requirements per object class. |  | Legal / Finance | Nice-to-have | Not started
1 · Inventory of truth | 08 | Freeze the source spreadsheets in a "before" backup folder. |  | IT | Critical | Not started
2 · Cleanse & normalize | 09 | De-duplicate customer master on tax ID + normalized name. | Matching on name alone is how you end up with three "ABC Trading." | Sales + Finance | Critical | Not started
2 · Cleanse & normalize | 10 | Standardize units of measure across product master. |  | Ops | Critical | Not started
2 · Cleanse & normalize | 11 | Validate currency codes against ISO-4217. |  | Finance | Must-do | Not started
2 · Cleanse & normalize | 12 | Resolve "unknown vendor" / "misc supplier" catch-all entries. |  | Procurement | Must-do | Not started
2 · Cleanse & normalize | 13 | Decide the cut-off rule for open vs. closed transactions. | Open as of which date? Counted in which period? Get finance to sign this in writing. | Finance | Critical | Not started
2 · Cleanse & normalize | 14 | Flag and isolate non-ASCII data that breaks downstream tools. |  | Data Lead | Must-do | Not started
2 · Cleanse & normalize | 15 | Scrub PII from non-production environments. |  | IT | Must-do | Not started
2 · Cleanse & normalize | 16 | Enrich missing GL codes against the new chart of accounts. |  | Finance | Critical | Not started
3 · Map & transform | 17 | Build source → target field map for every object you'll migrate. |  | BA + Tech | Critical | Not started
3 · Map & transform | 18 | Define default values for every required Odoo field with no source. |  | BA | Must-do | Not started
3 · Map & transform | 19 | Decide opening balance strategy: per-customer, per-account, per-product. |  | Finance | Critical | Not started
3 · Map & transform | 20 | Map taxes, fiscal positions and analytic tags. |  | Finance | Must-do | Not started
3 · Map & transform | 21 | Lock the external ID convention (__import__.<source>.<id>). |  | Tech | Must-do | Not started
3 · Map & transform | 22 | Translate UoM conversions where source & target differ. |  | Ops | Must-do | Not started
3 · Map & transform | 23 | Pre-compute lot/serial assignments for inventory on hand. |  | Warehouse | Nice-to-have | Not started
3 · Map & transform | 24 | Document one-way fields (no rollback path) prominently. |  | BA | Must-do | Not started
4 · Load & reconcile | 25 | Load order: company → COA → partners → products → BOMs → stock → open docs. |  | Tech | Critical | Not started
4 · Load & reconcile | 26 | Run dry run #1 against a copy of production config. |  | Tech | Critical | Not started
4 · Load & reconcile | 27 | Reconcile counts: source rows vs. target records, per object. |  | Data Lead | Must-do | Not started
4 · Load & reconcile | 28 | Reconcile sums: open AR, AP, stock value to the rupee/dollar. |  | Finance | Critical | Not started
4 · Load & reconcile | 29 | Spot-check 20 random records per object with the source owner. |  | BA + Owners | Must-do | Not started
4 · Load & reconcile | 30 | Document the time-to-load per object for the cutover plan. |  | Tech | Must-do | Not started
4 · Load & reconcile | 31 | Run dry run #2 with the actual cutover team and timing. |  | PM | Critical | Not started
4 · Load & reconcile | 32 | Capture every error message into a known-issue log. |  | Tech | Must-do | Not started
5 · Cutover & sign-off | 33 | Communicate freeze window to operations 14 days in advance. |  | PM | Must-do | Not started
5 · Cutover & sign-off | 34 | Take final source snapshot at T-0; lock write access. |  | IT | Critical | Not started
5 · Cutover & sign-off | 35 | Execute the load runbook, signing each step in real time. |  | Tech | Critical | Not started
5 · Cutover & sign-off | 36 | Reconcile balances against pre-cutover figures. |  | Finance | Critical | Not started
5 · Cutover & sign-off | 37 | Run the smoke-test script: 10 happy-path transactions, all modules. |  | BA | Must-do | Not started
5 · Cutover & sign-off | 38 | Get written sign-off from each module owner before re-opening operations. |  | PM | Critical | Not started
5 · Cutover & sign-off | 39 | Post the rollback playbook somewhere physical and visible. |  | PM | Must-do | Not started
5 · Cutover & sign-off | 40 | Schedule a 7-day, 30-day and 90-day reconciliation review. |  | BA + Finance | Nice-to-have | Not started
Critical items not yet done
Overall progress

## BD master data
Object | What to do | Bangladesh-specific fields to capture | Owner | Status | Notes
Customer master | Deduplicate (normalise Ltd/Limited), merge balances, flag inactive (2+ yrs) | BIN (for Mushak 6.3), email, phone, payment terms | Accounts | Not started
Vendor master | Deduplicate; classify for TDS | TIN (12-digit), TDS category/section, TDS rate (no-TIN = higher), BIN, bank account + BEFTN routing | Accounts | Not started
Product master | Consistent internal reference, category hierarchy agreed first | UoM (pcs, dzn, kg, yards), cost price at cut-over, product type, VAT treatment (15% / zero-rated / exempt), HS code for imports | Warehouse + Procurement | Not started
Chart of accounts | Map every legacy ledger to an Odoo account type; consolidate duplicates | VAT payable, input VAT, VDS, AIT/TDS payable, PF payable, gratuity provision | Accounts | Not started
Opening AR | Reconcile top-20 customers with statements; resolve disputes; decide on >180-day items | Per-invoice import preferred; total must match legacy TB to ৳1 | Accounts | Not started
Opening AP | Confirm top-20 vendor balances; reflect advances as debit balances | Per-bill import; supplier statements on file | Accounts + Procurement | Not started
Opening stock | PHYSICAL count, not system count; write off discrepancies with CFO approval first | Qty and unit cost per product per location; valuation = GL balance | Warehouse | Not started
Employee master | Accurate joining dates (gratuity), grades, PF status | NID, joining date, designation, basic/house rent/medical/conveyance, bank + routing | HR | Not started
Fixed assets | Cost, accumulated depreciation, NBV at cut-over | Category, acquisition date, method and rate, remaining life | Accounts | Not started
Open POs / SOs / LCs | Decide migrate vs. close in legacy; only outstanding quantities | Open LCs mapped to LC workflow; bills of entry referenced | Procurement + Sales | Not started

## Reconciliation
Object (load order) | Source count / sum | Odoo count / sum | Difference | Check | Checked by / notes
Chart of accounts
Customers
Vendors
Products
BOMs
Opening stock (qty)
Opening stock (value ৳)
Open AR (৳)
Open AP (৳)
Fixed assets (NBV ৳)
Employees
Open POs
Open SOs
Load order: company → chart of accounts → partners → products → BOMs → stock → open documents.