## About
Odoo Post Go-Live Hypercare Plan & Issue Log
What this is
Run the first weeks after go-live with a clear support model: severity SLAs, a single issue log, the first month-end close checklist, and objective exit criteria to move to business-as-usual.
How to use it
• Agree the severity definitions and SLAs with the partner before go-live.
• Log every issue in 'Issue log' and review it in the daily stand-up.
• Use 'Month-end close' for the first close in Odoo.
• Leave hypercare only when every item in 'Exit criteria' is met.
The full method behind this template
https://mhasan.me/lab/0032-odoo-post-go-live-hypercare-bangladesh
Yellow cells are for your input. Formulas are in plain cells, so avoid overwriting them.
Free template by Mehedi Hasan, Odoo Certified Functional Consultant · mhasan.me · Free to use and adapt; please keep this credit line.
Version: 25 September 2026

## Severity & SLA
Severity | Definition | Bangladesh examples | Response | Resolution
S1 — Critical | Operations stopped, no workaround | Cannot post vendor bills (tax config broken); cannot post GRN; server down; cannot generate Mushak 6.3 | 2 hours (any time) | 4 hours
S2 — High | Major function impaired, slow/error-prone workaround | TDS not calculating on bills; payroll wrong for one employee type; bank import failing for one bank | 4 hours | Same business day
S3 — Medium | Minor function impaired, easy workaround | Report missing a column; 6.3 print alignment off; dashboard default filter wrong | Next business day | 3 business days
S4 — Low | Cosmetic or enhancement | Bengali label requested; column order; out-of-scope convenience feature | Next business day | Post-hypercare backlog

## Support tiers
Tier | Who | Handles
L1 | Internal superusers | How-to questions, password resets, process clarification, report help, user-error recovery
L2 | Internal Odoo lead / partner functional | Configuration review, stuck workflows, data corrections, report/filter configuration, access rights
L3 | Partner consultant / developer | Defects and custom code bugs, developer-level configuration, performance, data integrity, integration failures

## Issue log
Issue # | Date / time | Module | Severity | Description | Reported by | Tier | Assigned to | Status | Resolved on | Root cause | Prevent recurrence
HC-001 | [7 empty] | Open

## Daily summary
Measure | Value
Open S1
Open S2
Open S3/S4
Resolved or closed
Share handled by L1 (superusers)

## Month-end close
# | Step | Owner | Status | Done on | Notes
1 | Bank reconciliation: all statement lines matched; charges and interest posted (target: 3 working days) |  | Not started
2 | AP/AR cut-off: all bills and invoices for the period posted; no drafts left |  | Not started
3 | Inventory valuation report = inventory asset account on the balance sheet |  | Not started
4 | Depreciation run posted (if Fixed Assets is live) |  | Not started
5 | Accruals and provisions reviewed: gratuity, leave encashment |  | Not started
6 | VAT: run the tax report; monthly one-third advance deposit calculated (quarterly return under Finance Act 2026) |  | Not started
7 | Lock the period (lock date) so nothing is back-dated |  | Not started
8 | P&L and balance sheet shared with sponsor/CFO and walked through |  | Not started

## Exit criteria
# | Exit criterion | Met? | Evidence | Confirmed by
1 | No S1/S2 issue open more than 24 hours in the last 5 consecutive business days
2 | Superusers (L1) resolve 80%+ of queries without L3 for 5 consecutive business days
3 | First month-end close completed in Odoo and financials confirmed by accounts
4 | First full payroll batch processed and approved without consultant involvement (if HR is live)
5 | 100% of in-scope daily transactions in Odoo; no parallel Tally/Excel records
6 | BAU support contract signed and support process communicated to all users
Ready to exit hypercare?