## About
Odoo Implementation Roadmap (12-week Gantt) & RACI
What this is
A 12-week, 5-phase roadmap for a Bangladesh SME implementation, with the RACI matrix and go/no-go criteria. Larger projects stretch each phase; the sequence stays the same.
How to use it
• Set your start date on 'Gantt' (cell B1); week headers update automatically.
• Adjust start week and duration per task; bars redraw via conditional formatting.
• Plan around Eid, Pohela Boishakh and fiscal year-end (June). Never go live in the week before Eid.
• Use 'RACI' to make ownership explicit before kick-off.
The full method behind this template
https://mhasan.me/lab/0028-odoo-implementation-roadmap-bangladesh
Yellow cells are for your input. Formulas are in plain cells, so avoid overwriting them.
Free template by Mehedi Hasan, Odoo Certified Functional Consultant · mhasan.me · Free to use and adapt; please keep this credit line.
Version: 25 September 2026

## Gantt
Project start date | 2026-11-01
Phase | Task | Start week | Weeks | Owner | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16
1 Discovery | Kick-off, roles, communication plan | 1 | 1 |  | Not started
1 Discovery | Process workshops (as-is) per department | 1 | 2 |  | Not started
1 Discovery | Gap analysis & signed requirements (BRD) | 2 | 1 |  | Not started
2 Configuration | Company, chart of accounts, taxes (VAT/SD/VDS/TDS) | 3 | 1 |  | Not started
2 Configuration | Inventory, purchase, sales configuration | 3 | 2 |  | Not started
2 Configuration | Manufacturing / payroll configuration | 4 | 2 |  | Not started
2 Configuration | Reports & print formats (Mushak 6.3, challan, payslip) | 5 | 2 |  | Not started
2 Configuration | Conference room pilot with key users | 6 | 1 |  | Not started
3 Data & UAT | Data cleansing & trial load #1 | 7 | 1 |  | Not started
3 Data & UAT | UAT cycle 1 with scripts | 8 | 1 |  | Not started
3 Data & UAT | Fixes, trial load #2 (timed), UAT cycle 2 | 9 | 1 |  | Not started
4 Training | Role-based training (Bangla where needed) | 10 | 2 |  | Not started
4 Training | Practical assessment & user sign-off | 11 | 1 |  | Not started
5 Go-live | Go/no-go meeting, freeze, physical stock count | 12 | 1 |  | Not started
5 Go-live | Cut-over & go-live | 12 | 1 |  | Not started
5 Go-live | Hypercare (continues 2–6 weeks) | 12 | 1 |  | Not started

## RACI
Activity | Sponsor (MD/CFO) | Client PM | Odoo consultant | Key users (dept heads) | IT admin
Scope sign-off | A | R | C | C | I
Business process documentation | I | A | R | R | I
Odoo configuration decisions | I | A | R | C | I
Server setup & user provisioning | I | A | C | I | R
Data extraction from legacy system | I | A | C | R | R
Data cleaning & validation | I | A | R | R | I
UAT test execution | I | A | C | R | I
Training delivery | I | A | R | R | I
Go-live decision | A | R | C | C | C
Hypercare issue escalation | I | A | R | R | C
R = Responsible (does it) · A = Accountable (one per row, signs off) · C = Consulted · I = Informed

## Go-no-go
# | Go-live criterion | Met? | Evidence / owner
1 | All Must UAT cases passed; no open S1/S2 defects
2 | Trial load #2 reconciled to the taka (AR, AP, stock value)
3 | Physical stock count completed and approved
4 | All users trained and signed off for their role
5 | Opening balances approved by finance
6 | Printers, scanners and internet (with backup link) tested at every site
7 | Hypercare roster agreed: who is on-site, which days
8 | Rollback plan documented and visible
9 | Not within 7 days before Eid / fiscal year-end
Decision