# Odoo Project Charter

One page that stops most ERP arguments before they start. Sign it before kick-off.

Template by Mehedi Hasan, Odoo Certified Functional Consultant · Method: https://mhasan.me/lab/0047-odoo-project-charter-template · Replace everything in [brackets].

# 1. Project identity

| Item | Detail |
| --- | --- |
| Project name | [e.g. Odoo ERP implementation — Phase 1] |
| Company / entities | [legal entities in scope] |
| Sponsor | [MD / CEO name] |
| Client project manager | [name, % time allocated] |
| Implementation partner & PM | [firm, name] |
| Charter version / date | [v1.0 — date] |

# 2. Objective — the business problem we are solving

[e.g. Implement Odoo Enterprise to replace Tally and manual Excel tracking across 3 manufacturing sites, so that stock, costing and VAT come from one system.]

# 3. Success criteria (measurable)

| KPI | Today (baseline) | Target | Measured when |
| --- | --- | --- | --- |
| Month-end close | [15 days] | [3 days] | [3 months after go-live] |
| Stock accuracy (count vs system) | [unknown] | [≥ 98%] | [first cycle count] |
| Mushak 6.3 / VAT return preparation | [2 days manual] | [same day from Odoo] | [first quarterly return] |
| [your KPI] |  |  |  |

# 4. Scope

In scope (this phase):

[Modules: Accounting, Inventory, Purchase, Sales, Manufacturing]

[Sites / companies]

[Bangladesh compliance: Mushak 6.3/9.1, VDS, TDS]

[Data migration: masters + opening balances + open documents]

[Integrations: bank statement import, biometric attendance]

Out of scope (explicitly):

[e.g. Payroll and HR — Phase 2]

[e.g. E-commerce integration]

[e.g. Migration of transaction history older than the current fiscal year]

# 5. Timeline and milestones

| Milestone | Target date | Sign-off by |
| --- | --- | --- |
| Discovery & gap analysis signed | [Month 1] | [Sponsor + key users] |
| Configuration complete / CRP | [Month 2] | [Client PM] |
| UAT passed & users trained | [Month 3] | [Process owners] |
| Go-live (go/no-go meeting) | [Month 4] | [Sponsor] |
| Hypercare exit | [Month 4–5] | [Client PM] |

# 6. Budget

| Cost line | Amount (৳) |
| --- | --- |
| Implementation fee |  |
| Odoo licence (year 1) |  |
| Hosting / hardware |  |
| Internal team time (opportunity cost) |  |
| Contingency (15–25%) |  |
| Total approved budget |  |

# 7. Governance

| Role | Name | Responsibility |
| --- | --- | --- |
| Project sponsor |  | Funds the project, resolves escalations, chairs go-live decision |
| Steering committee |  | Department heads; meets fortnightly; approves change requests |
| Client project manager |  | Day-to-day lead; makes sure the internal team tests and decides on time |
| Partner project manager |  | Delivery of the vendor's scope |
| Key users / champions |  | Define requirements, test (UAT), train colleagues, sign off |

Decision rule: process disputes not resolved by key users go to the steering committee and are decided within [48 hours].

# 8. Change control

Any change to scope, timeline or budget is raised as a written change request with cost and schedule impact, and approved by the steering committee before work starts.

# 9. Key risks

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Key users not released for testing |  |  | Protect 20–50% of their time in writing |  |
| Dirty master data |  |  | Start clean-up in discovery; trial loads |  |
| Scope creep |  |  | Change control; MoSCoW priorities |  |

# 10. Sign-off

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
|  | Project sponsor |  |  |
|  | Client project manager |  |  |
|  | Partner project manager |  |  |