## About
Odoo RFP — Vendor Scoring Matrix
What this is
Score Odoo implementation partners consistently on 14 weighted criteria. The highest total is your starting point for negotiation, not automatically the winner.
How to use it
• Disqualify any vendor that triggers a red flag (sheet 'Red flags') before scoring.
• Score each vendor 1–5 per criterion in the yellow cells, using the guidance column.
• Weighted score and total (max 500) calculate automatically.
• Call at least two references per shortlisted vendor using the questions sheet.
The full method behind this template
https://mhasan.me/lab/0029-odoo-rfp-template-bangladesh
Yellow cells are for your input. Formulas are in plain cells, so avoid overwriting them.
Free template by Mehedi Hasan, Odoo Certified Functional Consultant · mhasan.me · Free to use and adapt; please keep this credit line.
Version: 25 September 2026

## Scoring
Category | Criterion | Weight | Guidance (1 = weak · 5 = strong) | Vendor A score | Vendor A weighted | Vendor B score | Vendor B weighted | Vendor C score | Vendor C weighted
Bangladesh experience | Reference sites — industry match | 12% | 1 = no Bangladesh refs · 3 = refs in a different industry · 5 = verified refs in your industry, contacted and positive
Bangladesh experience | Bangladesh compliance demonstrated | 10% | 1 = claims capability, no demo · 3 = showed Mushak config in demo · 5 = live client using Mushak 6.3 + TDS + payroll
Bangladesh experience | Number of completed BD implementations | 8% | 1 = fewer than 3 · 3 = 5–10 · 5 = 15+ completed Bangladesh deployments
Project methodology | Quality of project plan presented | 10% | 1 = no plan / vague · 3 = plan exists, milestones unclear · 5 = week-by-week plan with named deliverables and decision points
Project methodology | UAT and testing approach | 8% | 1 = no formal UAT · 3 = described, no test scripts · 5 = provides test scripts, defect log, sign-off process
Project methodology | Training methodology | 7% | 1 = ad hoc · 3 = role-based described · 5 = role matrix, materials, assessment, sign-off sheet
Team quality | Lead consultant experience | 10% | 1 = no relevant experience · 3 = 2–4 years Odoo, mixed industries · 5 = 5+ years Odoo, multiple BD manufacturing projects
Team quality | Dedicated project manager | 6% | 1 = consultant is also PM · 3 = PM named but also consults · 5 = dedicated PM, CV provided, full-time
Team quality | Team continuity guarantee | 4% | 1 = no commitment · 3 = PM committed, consultant may change · 5 = named team committed in contract
Commercial terms | Price scope completeness | 7% | 1 = lump sum only · 3 = phase breakdown, some gaps · 5 = itemised by module + migration + training + support
Commercial terms | Payment milestone structure | 5% | 1 = large advance · 3 = 3-milestone structure · 5 = milestones tied to deliverables, final payment after stable go-live
Commercial terms | Post-go-live support terms | 3% | 1 = no support offer · 3 = described, no SLA · 5 = named SLA per severity, retainer option
Technical approach | Demo quality | 6% | 1 = PowerPoint · 3 = live Odoo, generic · 5 = live Odoo configured for your industry with BD compliance visible
Technical approach | Customisation approach | 4% | 1 = customises anything · 3 = standard first · 5 = clear framework for custom dev with documentation and upgrade path
TOTAL (max 500)
Rank

## Red flags
# | Red flag (any one = disqualify) | Vendor A (Y/N) | Vendor B (Y/N) | Vendor C (Y/N)
1 | Cannot name a Bangladesh reference site within 24 hours of being asked
2 | Proposes a fixed timeline without reviewing your data or customisation needs
3 | Cannot demo Bangladesh compliance (Mushak 6.3, TDS, payroll) live in a running Odoo instance
4 | No dedicated project manager: salesperson, PM and lead consultant are the same person
5 | Price more than 40% below other vendors with no specific explanation of scope difference
6 | Demands more than 30% advance payment
7 | Refuses to name the reviewed team members in the contract
Disqualified?

## Pre-qualification
Pre-qualification check (before sending the RFP) | Vendor A | Vendor B | Vendor C
Active Odoo partnership (Ready / Silver / Gold), verifiable on odoo.com
Can name a Bangladesh reference site in your industry
Team of at least 1 dedicated PM + 2 Odoo-certified consultants (for a 30–100 user project)

## Reference questions
# | Question (call, don't email) | Vendor A — reference answer | Vendor B — reference answer | Vendor C — reference answer
1 | On a scale of 1–10, how likely are you to recommend this vendor? What would it take to be a 10?
2 | Did the project finish on time and on budget? If not, what happened?
3 | What was the project team like day-to-day: responsive, proactive, or reactive?
4 | Were there any Bangladesh compliance issues (Mushak, TDS, payroll) the vendor struggled with?
5 | What happened in the first 2 weeks after go-live? Were they on-site?
6 | What would you do differently if you were selecting the vendor again?
7 | Is the same team still supporting you today?