## About
Odoo UAT Test Script Template
What this is
User acceptance testing scripts that test how real people work, not just happy paths. Every case names a person, a moment, a constraint, one variable forced off the happy path, and a measurable result.
How to use it
• Fill the header sheet once per UAT cycle.
• Write test cases in 'Test cases'. Sample Bangladesh cases are included, so replace them with yours.
• Log every failure in 'Defects' with a severity (S1–S4).
• 'Summary' counts progress automatically. Exit when all Must cases pass and no S1/S2 defects are open.
The full method behind this template
https://mhasan.me/lab/0009-uat-script-200-users-ago
Yellow cells are for your input. Formulas are in plain cells, so avoid overwriting them.
Free template by Mehedi Hasan, Odoo Certified Functional Consultant · mhasan.me · Free to use and adapt; please keep this credit line.
Version: 25 September 2026

## Header
Project
UAT cycle | Cycle 1
Environment / database | UAT copy of production config
Data used | Migrated trial-load data (dry run #2)
Start date
End date
Test lead
Sign-off by (process owners)

## Test cases
Case ID | Module | Priority | Persona & moment | Constraint / off-happy-path variable | Preconditions | Steps | Expected result (measurable) | If it fails, what does the user do? | Actual result | Status | Defect ID | Tester | Date
P2P-01 | Purchase | Must | Karim (procurement), month-end | Vendor quotes in USD; PO approved above ৳5 lakh limit | Vendor with TIN and TDS category set; approval rule active | 1. Create RFQ in USD 2. Confirm → approval triggered 3. Approve as manager 4. Receive partial quantity | PO needs approval; partial GRN leaves backorder; stock value = received qty × PO rate × exchange rate on receipt date
P2P-02 | Accounting | Must | Shila (AP), vendor bill day | Vendor is a service provider WITHOUT TIN | Vendor category 'Service — no TIN' | 1. Create vendor bill from PO 2. Post bill 3. Register payment | TDS at the no-TIN rate is deducted; payment = bill − TDS; TDS certificate data available
P2P-03 | Inventory | Must | Rahim (store), receiving an import | Landed cost: freight + CD + RD + SD arrive after the GRN | GRN posted; customs bill of entry available | 1. Create landed cost with CD, RD, SD, C&F charges 2. Split by value 3. Validate | Unit cost increases by landed cost; VAT/AT at import are NOT added to cost but go to VAT receivable
O2C-01 | Sales | Must | Nadia (sales), urgent order | Customer is over credit limit | Credit limit set on customer | 1. Create SO above limit 2. Try to confirm | Warning/block according to policy; manager override logged in chatter
O2C-02 | Accounting | Must | Tareq (accounts), invoicing a local sale | Customer is a VDS withholding entity | Customer BIN on record | 1. Validate delivery 2. Create invoice 3. Print Mushak 6.3 4. Record receipt net of VDS | 6.3 shows both BINs, VAT 15%; receipt with VDS leaves invoice fully paid and VDS receivable/6.6 tracked
O2C-03 | Sales | Must | Export desk | Export customer — zero-rated | Fiscal position 'Export — Zero VAT' | 1. Create SO for foreign customer 2. Invoice | Invoice at 0% VAT, shows in export (zero-rated) line of the tax report
MRP-01 | Manufacturing | Must | PPC planner, Monday plan | Component short for one MO | BOM with 3 levels; one RM below required qty | 1. Run replenishment 2. Confirm MO 3. Check availability | MO shows waiting; purchase RFQ generated for shortfall; no negative stock
MRP-02 | Manufacturing | Should | Line supervisor, end of shift | Actual consumption 3% above BOM | MO in progress | 1. Record actual consumption 2. Produce 3. Check cost | Variance visible; finished goods cost reflects actual consumption
HR-01 | Payroll | Must | HR officer, pay run | Worker joined 1 Dec 2023, 40 OT hours, 1 day absent | Wage-board grade structure configured | 1. Generate payslip 2. Check lines | Basic after increments; OT = basic÷208×2×hours; absence deduction applied; attendance bonus not paid
FIN-01 | Accounting | Must | Finance manager, first month-end | Bank statement has charges not yet booked | Statement imported | 1. Reconcile 2. Create write-offs for charges 3. Lock period | Bank balance = statement balance; lock date prevents back-dated entries
FIN-02 | Accounting | Must | Accounts, quarter end | Quarterly VAT return + monthly one-third advance deposits (Finance Act 2026) | Tax report configured | 1. Run tax report for the quarter 2. Compare with advances paid | Output VAT, input VAT, SD and net payable reconcile with GL; advances offset
SEC-01 | Access rights | Must | Store keeper | Tries to see product cost and vendor prices | Warehouse user group only | 1. Log in as store keeper 2. Open product, PO, valuation report | Cost fields and valuation menus are not visible

## Defects
Defect ID | Case ID | Date | Module | Severity | Description | Steps to reproduce | Reported by | Assigned to | Status | Fixed in | Retest result
D-001

## Summary
Measure | Value
Total cases
Passed
Failed
Blocked
Not started
Pass rate
Must cases not yet passed
Open S1 defects
Open S2 defects
UAT exit criteria met?